## Feuille 1
Tableau 1
| Action to be taken | Timeline | Teams | Subject | Content | Comments | Expectation Description | Expectation Name | Expectation Score | Done/To do
| Notify the exercise sponsor by SMS | M-5 | Sponsor | Cybersecurity exercise | Hello, the exercise starts at 09:00. Please remain available for decisions. | Use the crisis cell number; keep the message factual and concise. | Sponsor notified before start | Sponsor notification | 100 | To do
| Send an announcement email to executive management | 09:05 | Executive management | Exercise launch | An incident response exercise is starting. Objectives, duration, and Teams channel are provided in the attachment. | Clearly mention “Exercise” to avoid confusion. | Announcement message sent | Exec announcement | 100 | To do
| Open the crisis bridge (Teams/bridge) | 09:10 | Incident Commander | Crisis meeting | Teams link, access code, speaking and decision rules. | Create the channel; invite SOC/IT Ops/Comms/Legal. | Bridge operational < 5 min | Bridge opened | 100 | To do
| Activate the crisis cell | 09:15 | Crisis cell | Activation | Please join the bridge and acknowledge (R/A/A). | List of members and alternates attached. | Quorum reached in < 10 min | Crisis cell activation | 100 | To do
| Initial brief to SOC and IT Ops | T+2 | SOC, IT Ops | Initial alert | Network and web server anomalies detected (indicators provided). Prioritize triage. | Provide prepared IOCs and fake logs. | Initial triage started | Initial triage | 80 | To do
| Notify the Service Desk (user email) | 11:00 | AI Desk | Internal communication | Draft: possible slowdowns; investigation in progress; update in +30 min. | Validate with Comms and the Incident Commander. | Draft ready within 15 min | Internal comms ready | 25 | To do
Planner / Prepare the exercise
| Consolidate contacts and escalation paths | 12:00 | Planner | Crisis directory | Verify numbers, roles, on-call, and alternate channels. | Directory available in the planner/facilitator panel. | Directory verified and shared | Crisis directory | 100 | To do
| Prepare artifacts and materials (IOCs, fake logs, screenshots) | 12:30 | Planner/Red Team | Exercise artifacts | Indicator pack ready (hashes, domains, alert templates, screenshots). | Support available in the planner/facilitator panel. | Artifacts ready and tested | Artifact pack | 100 | To do
Facilitator / Run the exercise
| Send the initial alert to the SOC team by SMS | T-1 | SOC | Alert: IT system anomalies | Describe simulated symptoms and scope; provide IOC #1. | Timeline available in the planner/facilitator panel. | Alert sent | SOC alert | 100 | To do
| Inform executive management of the actual start by email | 16:00 | Executive management | Exercise start | The exercise starts now; situation updates every 30 minutes. | Preparing stimuli in advance saves time on the day. | Leadership informed | Leadership info | 100 | To do
| Observe and record key decisions | 16:05 | Observer | Observation | Note decisions, timelines, friction points, and escalations. | Use the provided observation grid. | Complete observations | Observation | 100 | To do
| Validate simulated remediation and record results | 17:00 | Incident Commander, Tech Leads | Remediation | Confirm measures (isolation, IOC blocking, patching, restoration) and expected outcomes. | Share the timeline with the facilitator; observation grid with the observer. | Remediation validated | Remediation | 100 | To do
Close the exercise
| Hold the hot debrief | 17:30 | All | Hot debrief | 30–45 min: key facts, strengths, improvement areas, immediate actions. | Debriefing support available in the planner/facilitator panel. | Debrief conducted | Hot debrief | 100 | To do
| Send the report and action plan by email | T+1 | IT Team, Executive management, Sponsors | Report | Consolidated report, action plan, owners and deadlines; follow-up scheduled. | Plan a cold debrief in 2–4 weeks; invite additional stakeholders if needed. | Report sent and actions tracked | Report + action plan | 100 | To do